## Tracker
Assignment Tracker
BIGGY |  | Design Enterprise Studio |  | Interaction Design | Mobile Apps
Plan Idea with finishing the proposal idea | Done | Update Website | Update Mobile Version | Go to locations and finalise decision | Finalise Idea
Write 1000 word proposal |  | Update Socials weekly (Linked in, instagram) | Last Edit 26th Sept | Plan out project | Divide and Conquer
Plan the project |  | Pricing Strategy |  |  | Individual work
|  | About me and Learning Contract | Done |  | Multichoice Exam 25%
|  | CV | Done
Client work
Task 0 - Initial Proposal | 2023-10-12 |  |  |  | Deadline - 11th January
Task 1 - Proposal (1000w) | 2023-10-26 |  |  |  | Our Deadline 1st of December
Task 2 - Poster | 2023-01-18
Task 3 - Report | 2023-04-25

## Dissertation
Dissertation
Weekly Planner |  | Submissions/Classes | Main Task | Achieved | Smaller Task | Achieved | Notes
Week 1 | 16th Oct
Week 2 | 23rd Oct
Week 3 | 30th Oct
Week 4 | 6th Nov
Week 5 | 13th Nov | Lecture | Read into camera angles and editing |  | Think into possible storyboard
Week 6 | 20th Nov |  | Read into lighting and music |  | Think into possible storyboard/create
Week 7 | 27th Nov |  | Create storyboard and find unity assets |  | Create GDPR forms
Week 8 | 4th Dec |  | Create unity scene
Week 9 | 11th Dec | Lecture | Create unity scene |  | Record unity scene, find music for scenes
Week 10 | 18th Dec |  | Edit scenes |  | Find participants to user tests
Week 11 | 25th Dec | CHRISTMAS
Week 12 | 1st Jan |  | Start designing poster |  | User testing
Week 13 | 8th Jan |  | Start poster presentation |  | User testing
Week 14 | 15th Jan | 15th Jan Poster Submission | Finish poster |  | User testing
Week 15 | 22nd Jan | 22nd Jan Poster Presentation | Poster presentation |  | User testing
Week 16 | 29th Jan |  | Storyboard advert |  | Find unity assets
Week 17 | 5th Feb |  | Create scene in unity
Week 18 | 12th Feb |  | Create scene in unity
Week 19 | 19th Feb |  | Record scene |  | Find music for scenes
Week 20 | 26th Feb |  | Edit scenes |  | User testing
Week 21 | 4th Mar |  | Edit changes from user testing |  | User testing
Week 22 | 11th Mar |  | Edit changes from user testing |  | User testing
Week 23 | 18th Mar | Lecture | Plan Report |  | Headings, subheadings, key references, key data
Week 24 | 25th Mar |  | Start Report |  | Get supervisor to look at worrying sections
Week 25 | 1st Apr |  | Start creation of report |  | Get supervisor to look at worrying sections
Week 26 | 8th Apr |  | Report |  | Get supervisor to look at worrying sections
Week 27 | 15th Apr |  | Report, video & soft submit |  | Get supervisor to look at worrying sections
Week 28 | 22nd Apr | 25th Report Submission | Submit |  | Get supervisor to look at worrying sections
SUBMISSION 25TH APRIL
Report
|  | Sections | Tasks
|  | Introduction | Overview of report and the outline (abstract)
|  | Section 1 | Pre-planning and secondary research
|  | Section 2 | User Testing (1st round)
|  | Section 3 | Wireframing, Figma Creation & Research
|  | Section 4 | User Testing (2nd round)
|  | Section 5 | Evaluation (went well & needs improvement)
|  | Conclusion | Findings and final verdict